## Sheet1
Schedule for report
| Date | Who | What
| 2018-04-30 | ALL | Recommender systems reading
| 2018-04-25 | ALL | EDA
| 2018-05-01 | Tharangni | Finishing EDA
| 2018-05-02 | Kishan | Finishing EDA, Evaluation function
| 2018-05-06 | Kishan | Benchmark Model
| 2010-05-18 | Tharangni | Preprocess - interpolate Null in orig_destination_distance
| 2018-05-07 | Kishan | RandomForest Model
| 2018-05-08 | Kishan | GradientBoosting Model
| 2018-05-10 | Kishan & Tharangni | Preprocessing Missing Values
| 2018-05-15 | Tharangni | Feature Engineering - Building composite values
| 2018-05-20 | ALL | Start working on the report
| 2018-05-20 | Kishan & Thomas | Hyperparameter Tuning
| 21/5/18 | Kishan & Tharangni | Feature Engineering - Relevant Features
| 2018-05-24 | ALL | Finishing report